## Summary
Project Name | : | Mahfil Mobile app
Project Manager | : | Tarqul Alam Opi
Project ID | :
Tester | : | SQTC
Test Case Preparation Date | :
Version | : | 1
Total scenarios | : | 41
Total Test case | : | 41
Test case with steps | :
Total Passed test case | : | 36
Total Failed test case | : | 0
Total blocked test case | : | 0
Total untested | : | 5
Total | : | 41

## Test_Scenarios
Test Scenario No. | User Type | Module | SubModule | Testing Category | Test Scenario | TC | POC | Priority | Planned Execution Date | Actual Execution Date
TS001 | User Authentication | Signup | Enter | UI and Functionality | Verify UI and Functionality of this module
TS002 |  |  | Verifying OTP | UI and Functionality | Verify UI and Functionality of this module
TS003 |  | SinIn | Enter | UI and Functionality | Verify UI and Functionality of this module
TS004 |  | Password Recovery | Enter | UI and Functionality | Verify UI and Functionality of this module
TS005 |  | User Profile | Update Profile | UI and Functionality | Verify UI and Functionality of this module
TS006 |  | LogOut | Enter | UI and Functionality | Verify UI and Functionality of this module
TS007 | Content Categories | Home | Waz, Nasheed, Tilawat, Islamic Shorts, Short Films, Halal Documentaries, and Funny Videos | Functional testing, UI/UX Testing, Content Validation, Performance Testing | Verify UI and Functionality of this module
TS008 |  | Lecture | Waz, Nasheed, Tilawat, Islamic Shorts, Short Films, Halal Documentaries, and Funny Videos | Functional testing, UI/UX Testing, Content Validation, Performance Testing | Verify UI and Functionality of this module
TS009 |  | Nasheed | Waz, Nasheed, Tilawat, Islamic Shorts, Short Films, Halal Documentaries, and Funny Videos | Functional testing, UI/UX Testing, Content Validation, Performance Testing | Verify UI and Functionality of this module
TS010 |  | Telawat | Waz, Nasheed, Tilawat, Islamic Shorts, Short Films, Halal Documentaries, and Funny Videos | Functional testing, UI/UX Testing, Content Validation, Performance Testing | Verify UI and Functionality of this module
TS011 |  | Others | Waz, Nasheed, Tilawat, Islamic Shorts, Short Films, Halal Documentaries, and Funny Videos | Functional testing, UI/UX Testing, Content Validation, Performance Testing | Verify UI and Functionality of this module
TS012 | Video Streaming | Home | Video Streaming, Different Types of Content, Buffering , Pause, Play and Autoplay | Feature Testing, Error Handling,Load Testing and Usability Testing. | Verify UI and Functionality of this module
TS013 |  | Lecture | Video Streaming, Different Types of Content, Buffering , Pause, Play and Autoplay | Feature Testing, Error Handling,Load Testing and Usability Testing. | Verify UI and Functionality of this module
TS014 |  | Nasheed | Video Streaming, Different Types of Content, Buffering , Pause, Play and Autoplay | Feature Testing, Error Handling,Load Testing and Usability Testing. | Verify UI and Functionality of this module
TS015 |  | Telawat | Video Streaming, Different Types of Content, Buffering , Pause, Play and Autoplay | Feature Testing, Error Handling,Load Testing and Usability Testing. | Verify UI and Functionality of this module
TS016 |  | Others | Video Streaming, Different Types of Content, Buffering , Pause, Play and Autoplay | Feature Testing, Error Handling,Load Testing and Usability Testing. | Verify UI and Functionality of this module
TS017 | Unique Video Content | Home | Videos and Others available Docoment | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Verify UI and Functionality of this module
TS018 |  | Lecture | Videos and Others available Docoment | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Verify UI and Functionality of this module
TS019 |  | Nasheed | Videos and Others available Docoment | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Verify UI and Functionality of this module
TS020 |  | Telawat | Videos and Others available Docoment | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Verify UI and Functionality of this module
TS021 |  | Others | Videos and Others available Docoment | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Verify UI and Functionality of this module
TS022 | Download Functionality | Home | Videos and Others available Docoment | Error Handling, Background Downloading,Download Status and Progress | Verify UI and Functionality of this module
TS023 |  | Lecture | Videos and Others available Docoment | Error Handling, Background Downloading,Download Status and Progress | Verify UI and Functionality of this module
TS024 |  | Nasheed | Videos and Others available Docoment | Error Handling, Background Downloading,Download Status and Progress | Verify UI and Functionality of this module
TS025 |  | Telawat | Videos and Others available Docoment | Error Handling, Background Downloading,Download Status and Progress | Verify UI and Functionality of this module
TS026 |  | Others | Videos and Others available Docoment | Error Handling, Background Downloading,Download Status and Progress | Verify UI and Functionality of this module
TS027 | Search and Filters | Home | Videos and Others available Docoment | Search and Filter Functionality Testing Integration Testing, Usability Testing | Verify UI and Functionality of this module
TS028 |  | Lecture | Videos and Others available Docoment | Search and Filter Functionality Testing Integration Testing, Usability Testing | Verify UI and Functionality of this module
TS029 |  | Nasheed | Videos and Others available Docoment | Search and Filter Functionality Testing Integration Testing, Usability Testing | Verify UI and Functionality of this module
TS030 |  | Telawat | Videos and Others available Docoment | Search and Filter Functionality Testing Integration Testing, Usability Testing | Verify UI and Functionality of this module
TS031 |  | Others | Videos and Others available Docoment | Search and Filter Functionality Testing Integration Testing, Usability Testing | Verify UI and Functionality of this module
TS032 | User Interaction | Home | Videos and Others available Docoment | Feature Testing, Notification Testing, Integration Testing | Verify UI and Functionality of this module
TS033 |  | Lecture | Videos and Others available Docoment | Feature Testing, Notification Testing, Integration Testing | Verify UI and Functionality of this module
TS034 |  | Nasheed | Videos and Others available Docoment | Feature Testing, Notification Testing, Integration Testing | Verify UI and Functionality of this module
TS035 |  | Telawat | Videos and Others available Docoment | Feature Testing, Notification Testing, Integration Testing | Verify UI and Functionality of this module
TS036 |  | Others | Videos and Others available Docoment | Feature Testing, Notification Testing, Integration Testing | Verify UI and Functionality of this module
TS037 | Performance Testing | Home | Videos and Others available Docoment | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Verify UI and Functionality of this module
TS038 |  | Lecture | Videos and Others available Docoment | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Verify UI and Functionality of this module
TS039 |  | Nasheed | Videos and Others available Docoment | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Verify UI and Functionality of this module
TS040 |  | Telawat | Videos and Others available Docoment | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Verify UI and Functionality of this module
TS041 |  | Others | Videos and Others available Docoment | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Verify UI and Functionality of this module

## Test_cases
Test Case Number | Test Case Name/Title | Description | Expected Result | Actual Result | Category | Test results | Defect ID | Defect Severity | Comments | Test Data | Planned Execution Date | Actual Execution Date | Firefox | Chrome | IE | Edge | Executed By | Browser Execution By
TS001_TC001 | Signup>Mobile No or Email No | Signup>Mobile No or Email No and Functionality View is working or not | It should work | It worked | Functional | Pass
TS002_TC001 | Signup>Mobile No or Email No>Continue | Signup>Mobile No or Email No>Continue Button and Functionality View is working or not | It should work | It worked | Functional | Pass
TS003_TC001 | Signup>Verifying OTP | Signup>Verifying OTP and Functionality View is working or not | It should work | It worked | Functional | Pass
TS004_TC001 | User login>Password Recovery | Verify if User login>Password Recovery is working or not | It should work | It worked | Functional | Pass
TS005_TC001 | User login>User Profile> Update Profile | Verify if User login>User Profile> Update Profile is working or not | It should work | It worked | Functional | Pass
TS006_TC001 | LogOut | Verify if LogOut is working or not | It should work | It worked | Functional | Pass
TS007_TC001 | Home>Slider Bar>Popular Channels> Tanding Videos | Verify if Home>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Functional Testing, UI/UX Testing, Content Validation, Performance Testing | Pass
TS008_TC001 | Lecture>Slider Bar>Popular Channels> Tanding Videos | Verify if Lecture>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Functional Testing, UI/UX Testing, Content Validation, Performance Testing | Pass
TS009_TC001 | Nasheed>Slider Bar>Popular Channels> Tanding Videos | Verify if Nasheed>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Functional Testing, UI/UX Testing, Content Validation, Performance Testing | Pass
TS010_TC001 | Telawat>Slider Bar>Popular Channels> Tanding Videos | Verify if Telawat>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Functional Testing, UI/UX Testing, Content Validation, Performance Testing | Pass
TS011_TC001 | Others>Slider Bar>Popular Channels> Tanding Videos | Verify if Others>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Functional Testing, UI/UX Testing, Content Validation, Performance Testing | Pass
TS012_TC001 | Home>Slider Bar>Popular Channels> Tanding Videos | Verify if Home>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Functional Testing, UI/UX Testing, Content Validation, Performance Testing | Pass
TS013_TC001 | Lecture>Slider Bar>Popular Channels> Tanding Videos | Verify if Lecture>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Feature Testing, Error Handling,Load Testing and Usability Testing | Pass
TS014_TC001 | Nasheed>Slider Bar>Popular Channels> Tanding Videos | Verify if Nasheed>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Feature Testing, Error Handling,Load Testing and Usability Testing | Pass
TS015_TC001 | Telawat>Slider Bar>Popular Channels> Tanding Videos | Verify if Telawat>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Feature Testing, Error Handling,Load Testing and Usability Testing | Pass
TS016_TC001 | Others>Slider Bar>Popular Channels> Tanding Videos | Verify if Others>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Feature Testing, Error Handling,Load Testing and Usability Testing | Pass
TS017_TC001 | Home>Slider Bar>Popular Channels> Tanding Videos | Verify if Home>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Pass
TS018_TC001 | Lecture>Slider Bar>Popular Channels> Tanding Videos | Verify if Lecture>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Pass
TS019_TC001 | Nasheed>Slider Bar>Popular Channels> Tanding Videos | Verify if Nasheed>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Pass
TS020_TC001 | Telawat>Slider Bar>Popular Channels> Tanding Videos | Verify if Telawat>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Pass
TS021_TC001 | Others>Slider Bar>Popular Channels> Tanding Videos | Verify if Others>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Content Review, Duplicate Content Check, Legal Compl iance,User Feedback Analysis | Pass
TS022_TC001 | Home>Slider Bar>Popular Channels> Tanding Videos | Verify if Home>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Error Handling, Background Downloading,Download Status and Progress | Untested
TS023_TC001 | Lecture>Slider Bar>Popular Channels> Tanding Videos | Verify if Lecture>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Error Handling, Background Downloading,Download Status and Progress | Untested
TS024_TC001 | Nasheed>Slider Bar>Popular Channels> Tanding Videos | Verify if Nasheed>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Error Handling, Background Downloading,Download Status and Progress | Untested
TS025_TC001 | Telawat>Slider Bar>Popular Channels> Tanding Videos | Verify if Telawat>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Error Handling, Background Downloading,Download Status and Progress | Untested
TS026_TC001 | Others>Slider Bar>Popular Channels> Tanding Videos | Verify if Others>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Error Handling, Background Downloading,Download Status and Progress | Untested
TS027_TC001 | Home>Slider Bar>Popular Channels> Tanding Videos | Verify if Home>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Search and Filter Functionality Testing Integration Testing, Usability Testing | Pass
TS028_TC001 | Lecture>Slider Bar>Popular Channels> Tanding Videos | Verify if Lecture>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Search and Filter Functionality Testing Integration Testing, Usability Testing | Pass
TS029_TC001 | Nasheed>Slider Bar>Popular Channels> Tanding Videos | Verify if Nasheed>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Search and Filter Functionality Testing Integration Testing, Usability Testing | Pass
TS030_TC001 | Telawat>Slider Bar>Popular Channels> Tanding Videos | Verify if Telawat>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It Didn't work | Search and Filter Functionality Testing Integration Testing, Usability Testing | Pass
TS031_TC001 | Others>Slider Bar>Popular Channels> Tanding Videos | Verify if Others>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Search and Filter Functionality Testing Integration Testing, Usability Testing | Pass
TS032_TC001 | Home>Slider Bar>Popular Channels> Tanding Videos | Verify if Home>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Feature Testing, Notification Testing, Integration Testing | Pass
TS033_TC001 | Lecture>Slider Bar>Popular Channels> Tanding Videos | Verify if Lecture>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It Didn't work | Feature Testing, Notification Testing, Integration Testing | Pass |  |  | file type filter not working
TS034_TC001 | Nasheed>Slider Bar>Popular Channels> Tanding Videos | Verify if Nasheed>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Feature Testing, Notification Testing, Integration Testing | Pass
TS035_TC001 | Telawat>Slider Bar>Popular Channels> Tanding Videos | Verify if Telawat>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Feature Testing, Notification Testing, Integration Testing | Pass
TS036_TC001 | Others>Slider Bar>Popular Channels> Tanding Videos | Verify if Others>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Feature Testing, Notification Testing, Integration Testing | Pass
TS037_TC001 | Home>Slider Bar>Popular Channels> Tanding Videos | Verify if Home>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Pass
TS038_TC001 | Lecture>Slider Bar>Popular Channels> Tanding Videos | Verify if Lecture>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Pass
TS039_TC001 | Nasheed>Slider Bar>Popular Channels> Tanding Videos | Verify if Nasheed>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Pass
TS040_TC001 | Telawat>Slider Bar>Popular Channels> Tanding Videos | Verify if Telawat>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Pass
TS041_TC001 | Others>Slider Bar>Popular Channels> Tanding Videos | Verify if Others>Slider Bar>Popular Channels> Tanding Videos is working or not | It should work | It worked | Load Testing, Video Playback Testing,Network Testing, Scalability Testing | Pass

## Defect-In-BugZilla
Bug ID | Severity | Severity | Status | Resolution | Summary | Actual Result | Expected Result | Steps To Reproduce | TC No. | Defect No. | Attachment

## Sheet1
3332 | DRM | Trivial | CONFIRMED | --- | Admin login ¦¦Management ¦¦User Management ¦¦+New User ¦¦It is not specified which fields are mandatory and which fields are not
3333 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Management ¦¦User Management ¦¦+New User ¦¦Blank spaces at 'Name' and 'User Name' field get accepted by the system
3334 | DRM | Major | CONFIRMED | --- | Admin ¦¦Management ¦¦User management ¦¦user edit ¦¦Duplicate user name can be set
3335 | DRM | Enhancement | CONFIRMED | --- | Admin ¦¦Management ¦¦User management ¦¦user edit ¦¦Deactivating and re-activating a user' feature is not available
3336 | DRM | Trivial | CONFIRMED | --- | Admin login ¦¦Management ¦¦Parliament member ¦¦+New User ¦¦It is not specified which fields are mandatory and which fields are not
3337 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Management ¦¦Parliament member ¦¦+New User ¦¦Blank spaces at 'Name' and 'Constituency' and 'Party' field get accepted by the system
3338 | DRM | Enhancement | CONFIRMED | --- | Admin login ¦¦Management ¦¦Parliament member ¦¦There should be Delete parliament member options available
3339 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Management ¦¦Room ¦¦+Add new room ¦¦Blank spaces at 'Name' get accepted by the system
3340 | DRM | Minor | CONFIRMED | --- | Admin login ¦¦Management ¦¦Committees ¦¦+Add new Committees ¦¦Clciking Submit buttpn without selecting any term get accepted and shows term as "0nth".
3341 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Management ¦¦Committees ¦¦+Add new Committees ¦¦Blank spaces at 'Name' get accepted by the system
3342 | DRM | Enhancement | CONFIRMED | --- | Admin login ¦¦Management ¦¦Committees ¦¦Spelling mistake-Term should be set as "12th' not as '12nth'
3343 | DRM | Normal | CONFIRMED | --- | Admin login ¦¦Proceedings ¦¦Committees ¦¦+Add new Proceedings ¦¦Blank spaces at 'Meeting name' get accepted by the system
3344 | DRM | Enhancement | CONFIRMED | --- | Admin ¦¦Proceeding ¦¦Add new proceeding ¦¦System should give warning message when duplicate data is being entered to prevent duplicate proceeding entry
3345 | DRM | Enhancement | CONFIRMED | --- | Admin ¦¦Proceeding/Recording ¦¦There should be searching and Filtering features of proceeding and recording
3346 | DRM | Enhancement | CONFIRMED | --- | Admin ¦¦Proceeding/Recording ¦¦There should be Delete proceeding and recording functionality
3347 | DRM | Major | CONFIRMED | --- | Admin/All user ¦¦Home ¦¦Scorilling doesnt work
3348 | DRM | Enhancement | CONFIRMED | --- | Admin/Director recording ¦¦Record ¦¦Clicking on Record Stop button should give confirmation message as once clicked record stop button by mistake Recording director can't resume the recording process
3349 | DRM | Major | CONFIRMED | --- | Admin ¦¦task management ¦¦If a Recording time is less than split time , that split of recording is not shown in task management audio split
3350 | DRM | Major | CONFIRMED | --- | Admin/Reporting officer ¦¦Transcription ¦¦Marking that has been done in recording module should be visible in transcription module while transcribing
3351 | DRM | Normal | CONFIRMED | --- | Reproting officer ¦¦ Transcribe ¦¦ Unicode and ANSI radio button is shown only in Admin UI not in Transcriber UI
3352 | DRM | Minor | CONFIRMED | --- | Reporitng officer ¦¦ Transcribe ¦¦ Shortcut key does not work for Reporting officer but for admin only
3353 | DRM | Normal | CONFIRMED | --- | Admin ¦¦Transcription ¦¦Compile report ¦¦Drafted portion should not be visible in admin panel to compile report or drafted portion should not be added in final report
3354 | DRM | Normal | CONFIRMED | --- | Director Reporting/Recording Supervisor ¦¦ Home ¦¦ "task Management" list is not visible in Home UI but visible in "Task Management UI" for Director Reporting
3355 | DRM | Enhancement | CONFIRMED | --- | All User ¦¦ Home ¦¦ user profile detail (name and role) should be visible at navbar when logged in

## Test steps
Test Case Number | Test Step ID | Test Steps | Expected Result | Test Results | Test Data

## Tracability Matrix
SNO | Requirement ID | Test Scenario | TestCase | Count

## Review Comment
SL No | Document name | Section name | Review Comment | Author name | Solution | Review Comment | Reviewed By | Reviewed Date | Status